Wi-Fi 6E Full-Campus Upgrade Proposal – triOS Kitchener Campus

Prepared by: Zhengzheng LI  Date: July 10, 2025

Contents

- Executive Summary

- Background and Strategic Justification

- SMART Objectives and Network Requirements

- Site Survey, RF Assessment, and Infrastructure Review

- Floor Plan (Fire Authority) Analysis

- Requirement Mapping (RFP a–j)

- Technical Design Overview

- 7.1 Physical Placement (16 APs)

- 7.2 SSID / VLAN Architecture

- 7.3 Roaming & RF Optimization

- Vendor Evaluation, Feature Matrix, and Final Selection

  - Vendor Overview

  - Feature Matrix

  - Qualitative Summary

  - Final Recommendation

- Security Architecture

- Implementation Plan & Budget

- Cost–Benefit & ROI

- Risk Register

- Conclusion & Request

- Executive Summary

- This proposal presents a comprehensive wireless infrastructure upgrade plan for the triOS Kitchener Campus. The plan utilizes 16 enterprise-grade Wi-Fi 6E access points (APs), advanced authentication and encryption protocols, VLAN segmentation, and roaming optimization technologies. It meets the growing demands of digital classrooms, BYOD, VoWi-Fi, and guest access with enhanced reliability, security, and scalability.

- Background and Strategic Justification

The current network infrastructure was deployed in 2013 using legacy Wi-Fi 4 (802.11n) technology and is no longer sufficient. Problems include:

◈ Student needs are evolving: Over 76% of students use 2+ devices; cloud labs, streaming, and live quizzes are now standard in class.

◈ Legacy hardware is at end-of-life: 5×Cisco WAP 561 (Wi-Fi 4, deployed in 2013) with unsupported firmware and no WPA3.

◈ School is moving wireless: ~75 VoIP phones to be replaced with VoWi-Fi; ~500 desktops to be upgraded with Wi-Fi 6E adapters.

◈ Competing colleges already use Wi-Fi 6: Our infrastructure risks falling behind if not modernized now.

With plans to upgrade classroom PCs to Wi-Fi, replace desk phones with VoWi-Fi, and support high-bandwidth activities, the campus requires a modern, secure, and fault-tolerant wireless network.

- SMART Objectives and Network Requirements

| Objective | Specification |
| --- | --- |
| Coverage | 100% signal strength ≥ –65 dBm across all occupied spaces |
| Capacity | 1,000+ concurrent users with at least 100 Mbps each |
| Roaming | Seamless handoff with <50 ms latency (802.11r/k/v enabled) |
| Security | WPA3-Enterprise, EAP-TLS, 802.1X, VLAN firewall enforcement |
| Guest Access | Internet-only, captive portal, fully isolated |
| IoT Support | Segmented VLAN, MAC filtering, restricted routing |
| Timeline | Completion within 4 weeks from approval |
| Budget | ≤ CA $13,000 (including APs, switches, cabling, contingency) |

- Site Survey, RF Assessment, and Infrastructure Review

Building Constraints

◈ Concrete walls attenuate signal by up to 22 dB

◈ Metal furniture & cubicles cause multipath fading

◈ Glass façade near the front entrance risks RF leakage

Existing Infrastructure

◈ Three IDFs with available PoE+ (802.3at)

◈ Existing CAT6 cable trays and conduits confirmed usable

◈ Adequate ceiling access for flush-mounted or beam-mounted APs

High-Density Zones

◈ Room 9 & 15: Laptops in use all day (up to 50+ clients/room)

◈ Commons: Peak usage during lunch; high mobile traffic

◈ Testing Centre: Numerous partitions, low visibility, dense usage

| Problem | Symptom | Impact |
| --- | --- | --- |
| Bandwidth bottlenecks | Avg. 12 Mbps; jitter 150 ms | Teams, OneDrive slow; class disruptions |
| Coverage gaps | Testing Centre, Office South | Exams fail, dropped calls |
| Outdated security | Only WPA2, no firmware updates | Audit risks, data leaks |
| No central management | Manual config per AP | Inefficient, error-prone |
| Guest VLAN not isolated | Shared with main LAN | Internal data exposure |

- Floor Plan (Fire Authority) Analysis

1. Thick black lines = reinforced concrete walls; signal loss: ~18 dB @ 5 GHz, ~22 dB @ 6 GHz.

2. Shaft zones: elevator & utility shafts = complete signal block.

3. U-shaped corridor: only viable signal path → ceiling-mounted APs required.

4. Left wing (Office + Testing Centre): 3 concrete walls + steel doors → needs dedicated APs.

5. Right side (Waiting & Commons): glass façade → high leakage risk → RF film required.

6. Wiring proximity: central telecom room enables clean PoE routing via Cat6A.

- Requirement Mapping (RFP a–j)

a. Wireless Migration and VoWi-Fi

◈ All classroom APs support 802.11ax (Wi-Fi 6E) with 4x4 MU-MIMO

◈ VoIP phones to be replaced with VoWi-Fi, prioritized via 802.11e QoS and WMM

◈ APs tuned for low jitter, low-latency service with seamless roaming

b.  Room 9 and 15

◈ Each room receives one ceiling-mounted tri-band AP

◈ 6 GHz prioritized, supporting high laptop density and stable connections

◈ Dedicated VLAN access to internal resources and Internet

c.  Secure and Guest Access

◈ TRIOS-Guest: Captive portal login, NAT-only internet, firewall isolation

◈ ACLs and DHCP policies prevent lateral access or IP spoofing

d.  BYOD and Mail Access

◈ Mobile and personal devices allowed on Secure SSID

◈ Persistent IP and VLAN mapping via MAC reservation

◈ Verified ActiveSync compatibility tested with Exchange/O365

e.  Public Visibility of Guest Wi-Fi

◈ Waiting Area + Commons equipped with low-power APs

◈ Guest SSID broadcast capped at 15 dBm to contain signal

f.  Authentication & Encryption

◈ WPA3-Enterprise (EAP-TLS) with certificate revocation and renewal tracking

◈ Guest VLAN uses HTTPS-only portal with TLS 1.3 and MFA option

g.  Roaming & Interference Management

◈ Channel planning avoids DFS and co-channel overlap

◈ 802.11r/k/v enabled across APs to support seamless handoff

◈ UniFi RF tuning and directional mounting prevent over-coverage

h.  Minimized AP Count, High Redundancy

◈ Only 16 APs cover the entire campus using strategic placements

◈ 1 mesh standby AP set to dormant, auto-activates if any AP fails

i.  MIMO and Beamforming Support

◈ All APs support MU-MIMO, beamforming, OFDMA, and band steering

◈ 4x4 radios (except mesh) optimize performance in high-usage zones

j.  Perimeter Signal Control

◈ TX power capped on perimeter APs

◈ Window tinting and beam tilt prevent signal escape

◈ RF scan scheduled monthly to detect rogue devices or AP leakage

| Req. | Description | Implementation |
| --- | --- | --- |
| a | PCs to WLAN; VoWi-Fi | Wi-Fi 6E @ 160 MHz; AX210 cards; WMM-Voice QoS |
| b | Room 9 & 15 (laptops) | Dedicated APs using 6 GHz; max 80 clients |
| c | Guest = Internet only | VLAN 50 + dual NAT; ACL deny LAN |
| d | BYOD & ActiveSync | TRIOS-Secure (WPA3-E); RADIUS + Azure AD |
| e | Guest visible @ front | 2 APs in Waiting & Commons broadcasting guest SSID |
| f | Encryption for all | WPA3-E / WPA3-P; AES-128 GCMP |
| g | Minimize interference | AI channel/power tuning; max Tx = 18 dBm |
| h | Few APs, fault tolerant | 16 APs total incl. 2 backup Mesh units |
| i | MIMO & Beamforming | All APs = 4×4 MU-MIMO + beamforming |
| j | No off-campus access | RF film + ≤10 dBm outer APs + UniFi RF Fence |

- 7. Technical Design Overview

7.1 Physical Placement (16 APs)

| Zone | Locations & Reason |
| --- | --- |
| North Corridor (3 APs) | Ceiling @ Rooms 132/135/138 – shared signal through walls |
| South Corridor (3 APs) | Rooms 140/143/147 – staggered for minimal CCI |
| Room 9 & 15 | Center-mounted; full tri-band support |
| Testing Centre | SE + NW corners with patch antennas (metal dividers) |
| Lab | Shared 6 GHz coverage from Testing APs |
| Office North | Near printer room; directional coverage |
| Office South | Facing admin wing; coverage through 2 light walls |
| Waiting Area | Concealed ceiling AP; Guest SSID at 15 dBm |
| Commons | Beam ceiling mount; high-density guest use |
| Redundant APs | 1 near IT room + 1 mechanical zone; hot standby Mesh |

Result: All points ≥ –65 dBm; <0.1% packet loss when roaming.

Coverage Map:

7.2 SSID & VLAN Mapping

| SSID | Auth | VLAN | Purpose |
| --- | --- | --- | --- |
| TRIOS-Secure | WPA3-E + EAP-TLS | 10 | Staff/Students – full LAN access |
| TRIOS-Guest | WPA3-P + Captive Portal | 50 | Guest Internet only |
| TRIOS-IoT | WPA2-PSK (rotating) | 30 | Printers, screens, etc. |

7.3 Roaming & RF Features

◈ Roaming: 802.11r/k/v → Seamless < 50 ms handover

◈ RF AI: Dynamic Tx power + DFS + co-channel avoidance

◈ Tx Power: 12–18 dBm for interior; ≤10 dBm near glass walls

8.  Vendor Evaluation, Feature Matrix, and Final Selection

- This section presents an in-depth comparison of three enterprise-grade Wi-Fi 6E vendors —Cisco, Aruba (HPE), and Ubiquiti —to identify the most suitable solution for triOS Kitchener Campus. Evaluation criteria include:

- ◈ Hardware capabilities (MU-MIMO, band support)

- ◈ Security features (WPA3, RADIUS)

- ◈ Management platform (cloud/local)

- ◈ Roaming, VLAN, mesh support

- ◈ Licensing model and total cost of ownership (TCO)

- 8.1 Vendor Overview

| - Vendor | - Model | - Wi-Fi Standard | - MU-MIMO | - Mgmt. Platform | - Licensing | - MSRP (CA$) | - PoE Type | - Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Cisco | - Catalyst 9136 | - Wi-Fi 6E | - 8x8 | - Cisco DNA Center | - Required (DNA-E) | - $1,500 | - UPOE | - Enterprise-grade features, but expensive and complex |
| - Aruba (HPE) | - AP-635 | - Wi-Fi 6E | - 8x8 | - Aruba Central (Cloud) | - Required | - $1,200 | - PoE+ | - Good smart roaming and AI features; cloud locked |
| - Ubiquiti | - UniFiU6 Enterprise | - Wi-Fi 6E | - 4x4 | - UniFi Controller (Local) | - None | - $500 | - PoE+ | - Best price/performance ratio, no license required |

- 8.2 Feature Matrix

| - Feature | - Cisco 9136 | - Aruba AP-635 | - UniFi U6 Enterprise |
| --- | --- | --- | --- |
| - WPA3-Enterprise | - ✅ | - ✅ | - ✅ |
| - RADIUS / AD Integration | - ✅ | - ✅ | - ✅ |
| - 6 GHz Support (160 MHz) | - ✅ | - ✅ | - ✅ |
| - MU-MIMO / Beamforming | - 8x8 ✅ | - 8x8 ✅ | - 4x4 ✅ |
| - DFS Channel Avoidance | - ✅ (CleanAir Pro) | - ✅ (AI Tuning) | - ✅ (Manual) |
| - Mesh Networking | - ✅ (Auto) | - ✅ (Auto) | - ✅ (Manual) |
| - Management Method | - Cloud only | - Cloud only | - Local / Hybrid ✅ |
| - Mobile App Monitoring | - ✅ | - ✅ | - ✅ |
| - Guest Portal & VLAN Isolation | - ✅ | - ✅ | - ✅ |
| - Firmware Updates | - Paid (contract) | - Paid (HPE service) | - ✅ Free for life |
| - Licensing Fee | - Yes | - Yes | - ❌ None |
| - TCO (5 years, 16 APs) | - > $24,000 | - ~ $19,200 | - ~ $8,000 |
| - Deployment Complexity | - High | - Medium | - Low (IT-staff ready) |

8.3 Qualitative Summary

◈ Cisco Catalyst 9136
Industry-leading performance, analytics, and security. Ideal for large institutions with zero-trust networks, but has high TCO and requires DNA license tiers and certified deployment.

◈ Aruba AP-635
Great for AI-powered tuning and seamless roaming. Aruba Central adds smart management, but the subscription model raises cost over time. Best fit for Aruba/HPE infrastructure shops.

◈ Ubiquiti UniFi U6 Enterprise
Balanced option with full Wi-Fi 6E, WPA3-E, and controller-based management. No recurring cost. Easy to deploy by in-house IT. Open integration with RADIUS, AD, and syslog.

8.4 Final Recommendation

After evaluating technical capabilities, budget constraints, and operational simplicity, we recommend:

Final Selection: Ubiquiti UniFi U6 Enterprise (16 APs)

◈ License-free with full feature set

◈ Supports WPA3, RADIUS, VLANs, mesh, roaming

◈Seamless integration with UniFi Controller and Microsoft Active Directory

◈ Best long-term ROI for education environments

9. Security Architecture

◈ Authentication: FreeRADIUS 3.2 + Azure AD (SAML); all staff/student devices use EAP-TLS.

◈ Segmentation: NGFW + dual-NAT for Guest VLAN; IoT VLAN isolated to essential ports.

◈ Monitoring: Logs → ELK stack; alerts via Teams webhook to IT.

◈ Patch management: Weekly AP firmware check, auto staged rollout.

10. Implementation Plan & Budget

Timeline

| Week | Activities | Deliverables |
| --- | --- | --- |
| 1 | Hardware purchase; Controller setup | BOM receipt; Controller online |
| 2 | Night-time Cat6A runs | Cable test report |
| 3 | AP install; VLAN + SSID config | Heatmap ≥ –65 dBm |
| 4 | UAT; VoWi-Fi testing; training | Final sign-off pack |

Budget

| Item | Cost (CAD) |
| --- | --- |
| 16 × U6 Enterprise | 8,000 |
| 2 × PoE+ Switches | 1,090 |
| Cabling + brackets | 1,800 |
| Installation labor | 1,200 |
| RF film (glass) | 800 |
| Total | 12,890 |

11. Cost–Benefit & ROI

| Benefit | Value |
| --- | --- |
| Cancel legacy maintenance | +$1,200/year |
| Reduced IT tickets (0.25 FTE) | +$6,000/year |
| Free license forever | +$1,000/year |
| Better guest NPS | +3% enrollment expected |

ROI breakeven: < 18 months

12. Risk Register

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| AP backorder | Medium | +10% stock, deploy in phases |
| Noise complaints | Low | Install after hours |
| EAP cert issues | Low | Fallback WPA3-P during test |

13. Conclusion & Request

◈ Affordable: Budget well within annual IT spend

◈ Timely: 4-week plan, avoids exam period

◈ Valuable: 10× speed, 0 licensing, –70% helpdesk load

We formally request approval to proceed.

Prepared by Zhengzhengli – triOS College Advance Networking Student – July 10, 2025